## Trang tính1
Iteration | Ouput | Task | In-charge | Deadline | Status | Note
Iteration#0 | SRS Overview | Introduction | Viet | 2021-09-12 | Completed
|  | Function for Marketing feature | Thinh | 2021-09-12 | Completed
|  | Screen Detail | Nam | 2021-09-12 | Completed
|  | User Authorization | Hieu | 2021-09-12 | Completed
|  | Non-Screen Function | Quang | 2021-09-12 | Completed
| Product Backlog | Function for Admin feature | Nam | 2021-09-12 | Completed
|  | Function for Common feature | Nam | 2021-09-12 | Completed
|  | Function for Public feature | Thinh | 2021-09-12 | Completed
|  | Function for Marketing feature | Thinh | 2021-09-12 | Completed
| Vertical Prototype | Code Login Page | Nam | 2021-09-17 | Completed
|  | Code Home Page | Thinh | 2021-09-17 | Completed
|  | Code Admin Dashboard | Hieu | 2021-09-17 | Completed
|  | Code User Profile | Quang | 2021-09-17 | Completed
|  | Code User Management | Viet | 2021-09-17 | Completed
| Design Overview | Code Package/Namespace | Thinh | 2021-09-19 | Completed
|  | Database Schema | Quang | 2021-09-19 | Completed
|  | Table Description | Quang | 2021-09-19 | Completed
|  | Class Diagram | Hieu | 2021-09-19 | Completed
|  | Class Specifications | Hieu | 2021-09-19 | Completed
|  | Sequence Diagram | Viet | 2021-09-19 | Completed
|  | Database Queries | Viet | 2021-09-19 | Completed
| Plan for Iteration 1 | Finish Code Login, Logout, Register, Forgot & Change Password Page | Nam | 2021-09-25 | On-going
|  | Code Home Page | Thinh | 2021-09-25 | On-going
|  | Code Admin | Hieu | 2021-09-25 | On-going
|  | Code Product | Quang | 2021-09-25 | On-going
|  | Code User profile | Viet | 2021-09-25 | On-going
|  | Update SRS | Nam | 2021-10-02 | Not yet
|  | Update Vertical Prototype | Viet | 2021-10-02 | Not yet
|  | Update database | Quang | 2021-10-02 | Not yet
|  | Update Design Overview | Thinh | 2021-10-02 | Not yet
|  | Update Product Backlog | Hieu | 2021-10-02 | Not yet